## Task List
DRAFT VERSION FOR INDIANA 02.20.12
PHASE 2B - MAPPING-DRAFT 02.20.12
Status | Task | Explanation | Actions | Guidance | Comments
Map Scale - Review Specifications
| Calculate Final Map Display scale | Calculate the final intended map display scale based upon the underlying terrain data set DEM cell size. The map display scale will be calculated by multiplying the DEM grid cell diameter (in meters) by 2,000 pixels/meter to get the standard display scale in a standard 1 inch = X feet or 1:X ratio. The QC review will occur at the final map display scale. The final map display scale will be also be used to set the Google Maps zoom level. | NWS will calculate the Map display scale and enter in the header of the Project Development Template. | 3.6
| NWS Flood Inundation Mapping Tools for GIS | A set of QC tools are available from the NWS to review GIS data. NWS will provide a copy of the tools to Technical Partner and provide instructions on how to install and operate tools. | NWS will provide Technical Partner with a copy of "NWS Flood Inundation Mapping Tools" for ESRI ArcGIS 10.0. | N/A
| Conduct Map Review at the Pre-determined Map Display Scale | Check Polygons and Depth Grids for visible errors at the final map display scale that was determined in Phase 2B. Errors that are visible at a scale larger than the intended map scale (i.e. zoomed in beyond the intended scale) will not require correction. NWS will check the map at the final display scale and will not zoom in beyond this display scale to review data for errors. | Technical Partner and NWS QC Team will review the depth grids for visible errors at the final map display scale. | 3.6
Depth Grid Raster - Review Specifications
| WSEL Boundary Checks | Perform reasonability check with WSEL boundary shapefiles, orthophotography, and rasters /contours. Ensure transitions along the boundary are consistent with the raster/contour data. Ensure that a terrain DEM was used to resample or downscale from a larger grid cell size to a smaller grid cell size. Ensure that the water surface is in good agreement with physical structures visible in the orthophoto, flood protection structure centerlines and other ground reference data. Verify using tools such as Google Maps and Bing Maps oblique photography. Errors should not be visible at the Final Map Display Scale. | Technical Partner will submit grid inundation layers formatted to specifications described in Project Development Template. | 3.3 | DONE
| Flood Impact Evaluation | Compare inundation maps to NWS impact statements documented on AHPS and in the [Flood Impacts] tab and verify that the NWS Impact statements for the AHPS forecast point are in agreement with the inundation mapping layers. Errors should not be visible at the Final Map Display Scale. | Technical Partner will submit grid inundation layers formatted to specifications described in Project Development Template. | N/A | DONE
| FEMA DFIRM Agreement (OPTIONAL) | Check agreement with FEMA Flood Insurance Study DFIRM (if available and current), should reasonably agree with the corresponding grid and polygon layers. This check is OPTIONAL for projects where a DFIRM is not available or the DFIRM not be published on AHPS. | Technical Partner will submit grid inundation layers formatted to specifications described in Project Development Template. | 5.2.3.1 | DONE
| Bankfull Check | Ensure lowest WSEL polygon covers stream and channel banks visible from orthophotography. Errors should not be visible at the Final Map Display Scale. | Technical Partner will submit grid inundation layers formatted to specifications described in Project Development Template. | N/A | DONE
| Higher\Lower Boundary Comparison | The boundaries of higher WSEL depth grids contain or match the boundaries of lower WSEL depth grids. Errors should not be visible at the Final Map Display Scale. The "NWS Flood Inundation Mapping Tools" GIS Toolbox contains a "Polygon Overlap QC Batch\Single" tool that should be run for each layer to identify overlaps. Polygons will need to be created prior to running the tool. | Technical Partner will submit grid inundation layers formatted to specifications described in Project Development Template. Technical Partner and NWS should use the "NWS Flood Inundation Mapping Tools" GIS Toolbox contains a "Polygon Overlap QC Batch\Single" tool . | 3.3 | DONE
| Disconnected Wetted Areas | Remove wetted areas that result from depressions that are not hydraulically connected to the studied flow in the main river channel. Areas that are directly connected via storm sewers are acceptable. Errors should not be visible at the Final Map Display Scale. | Technical Partner will submit grid inundation layers formatted to specifications described in Project Development Template. | 3.3 | DONE
| Dry Flood Control Structures | Verify that the impacts from all flood control structures published in the [Structures] tab are displayed per NWS specifications. Check that the depth grids are coincident with and do not overlap the levee, floodwall and temporary measures centerlines when the landward size of the structure is dry. The structures should be checked for all elevations where overtopping does not occur and for all elevations where the toe of the structure is wet, but overtopping does not occur. Errors should not be visible at the Final Map Display Scale. | Technical Partner will submit grid inundation layers formatted to specifications described in Project Development Template. | 3.3.1
| Wet Flood Control Structures | Verify that the impacts from all flood control structures published in the [Structures] tab are displayed per NWS specifications. Review the impacts on the landward side of a flood control structure, after the structure overtops. 1-D Model Case: Depth grids created by a 1-D model should display a uniform and generalized risk area, on the landward side, for all elevations above the overtopping elevation. Depth values should be set to a uniform missing value. 2-D Model Case: Depth grids created by 2-D models should display unique depth grid layers, on the landward side, for each overtopped elevation. Depth values should be displayed as modeled. Errors should not be visible at the Final Map Display Scale. | Technical Partner will submit grid inundation layers formatted to specifications described in Project Development Template. | 3.3.1
| Bridge Decking Removal | Bridges should be clipped when water first touches either the low chord elevation or the approach to the bridge. The lowest elevation (approach or low chord) should be used as the basis for defining the elevations to stop\start clipping. Bridges that have been clipped should have the depth grids set to NoData in the clipped area. A wide enough swath of cells should be clipped so that the bridge decking is fully and clearly visible when clipped. Errors should not be visible at the Final Map Display Scale. | Technical Partner will submit grid inundation layers formatted to specifications described in Project Development Template. | 3.3.2 | DONE
| Bridge Overtopping | The depth of flow for elevations above the low chord, that are overtopped by flow should be representative of the total depth of flow in the channel. Errors should not be visible at the Final Map Display Scale. | Technical Partner will submit grid inundation layers formatted to specifications described in Project Development Template. | 3.3.2
| Ponds, Lakes and Bodies of Water Check | Depth grid and polygons boundaries are consistent with the boundaries around ponds, lakes and other bodies of water affected by the flooding. Errors should not be visible at the Final Map Display Scale. | Technical Partner will submit grid inundation layers formatted to specifications described in Project Development Template. | N/A | DONE
| Representative Depth Check | Depth grid raster values are reasonable and representative of the depth of flow between the modeled WSE and the terrain. Technical Partner and NWS should spot check depth measurements and review the color shaded depth grids closely. Errors should not be visible at the Final Map Display Scale. | Technical Partner will submit grid inundation layers formatted to specifications described in Project Development Template. | N/A | DONE
| Positive Depth Check | Ensure that wetted areas have positive depths and non-wetted area depths are set to missing values. | Technical Partner will submit grid inundation layers formatted to specifications described in Project Development Template. | N/A | DONE
Inundation Polygon - Review Specifications
| Polygon & Grid Pairing | Ensure there is a corresponding depth grid raster file(s) for each Inundation polygon file(s). | Technical Partner will submit polygon and grid inundation layers formatted to specifications described in Project Development Template Description. | N/A | DONE
| Polygon & Grid Consistency | Each polygon will be an exact copy of the depth grid. Polygons should not be smoothed or interpolated to remove the jagged or rectilinear edges. | Technical Partner will submit polygon and grid inundation layers formatted to specifications described in Project Development Template Description. Technical Partner and NWS should use the "NWS Flood Inundation Mapping Tools" GIS Toolbox contains a "Polygon Grid QC Batch\Single" tool . | N/A | DONE
Mapping File Management - Review Specifications
| Projection | Set the coordinate system for shapefiles and rasters to World Geodetic System of 1984 (WGS84) | Technical Partner will submit all GIS layers projected to a World Geographic System of 1984 (WGS84) geographic projection. | 3.3 | DONE
| Naming Convention | Verify that file naming convention used for base mapping data, inundation polygons and depth rasters layers conforms to required naming conventions. Naming conventions are identified by the {bracketed names.shp} present in the Final Deliverables Check List. | Technical Partner will submit GIS layers formatted to the naming specifications described in for each deliverable. | N/A | DONE
| Metadata | Review and verify that metadata is attached to all GIS data and meets FGDC standards. Enter metadata using the ESRI ArcCatalog application. Verify that the metadata fields and text that are published in the [Metadata] tab have been added to the corresponding data set. | Technical Partner will create new metadata or verify that existing metadata is attached to all GIS data and meets FGDC standards. Partner will enter and attach metadata to the shapefiles and grids using the ESRI ArcCatalog application. Metadata will include elements listed in the [Metadata] tab. | 3.1.9 | DONE
| File Structure | Each deliverable will be submitted and organized according to a standard file structure and naming convention outlined in the [File Structure] tab. | Technical Partner will format deliverable according to the [File Structure] tab. | N/A | DONE
USGS Project Approval
| USGS Project Approval (OPTIONAL) | Obtain Bureau approval for geospatial data and publications (if applicable). See [USGS Approval] tab for more detail. This is applicable only to USGS projects. | USGS Projects will obtain Bureau approval and follow procedures in [USGS Approval] tab. | N/A | in progress
Project Management
Not Applicable | Update Project Timeline | Update the project status in the Gantt chart in the [Timeline] tab, and inform all team members of the status of the project. | NWS and Technical Partner will update the estimate of the project tasks in the Gantt chart in the [Timeline] tab. | 2.1
Not Applicable | Update the Project Development Template | Update the Project Development Template. | NWS Coordinator will update the Project Development Template. | N/A
Not Applicable | Verify AHPS Funding Received | Verify that Orion Technologies has received AHPS funding. Phase 3 activities cannot begin until funding has been received. | NWS Coordinator will coordinate with Orion Technologies and the funding source to verify that funding has been sent and received prior to starting Phase 3. | N/A
Phase 2B Deliverable Checklist
GIS Data Deliverables
| STUDY AREA {study_area.shp} Format: Line shapefile (REQUIRED) | This is the “Brown Line” on AHPS. Model extent line file shows the extent of the hydraulic model that is included within the AHPS mapping area. The study area extents should align with cross-sections on the hydraulic model. | Technical Partner will deliver layer in (1) shapefile format,(2) with FGDC compliant metadata attached by using ESRI ArcCatalog, Metadata will include elements listed in [Metadata] (3) in a WGS84 projection (4) name files according to the standard-see {bracketed} example. Data will be delivered in a zip file and organized according to the [File Structure] tab. | 3.1 | DONE
| MODEL CROSS-SECTIONS {xs.shp} Format: Line shapefile (REQUIRED) | Include the hydraulic model cross-sections used to develop the inundation mapping. This will allow the modeling to be archived for future applications and updates to the inundation mapping. | Technical Partner will deliver layer in (1) shapefile format,(2) with FGDC compliant metadata attached by using ESRI ArcCatalog, Metadata will include elements listed in [Metadata] (3) in a WGS84 projection (4) name files according to the standard-see {bracketed} example. Data will be delivered in a zip file and organized according to the [File Structure] tab. | 3.1 | DONE
| GAGE LOCATION POINT {gage.shp} Format: Point shapefile (REQUIRED) | The location of the stream gage data collection point. | Technical Partner will deliver layer in (1) shapefile format,(2) with FGDC compliant metadata attached by using ESRI ArcCatalog, Metadata will include elements listed in [Metadata] (3) in a WGS84 projection (4) name files according to the standard-see {bracketed} example. Data will be delivered in a zip file and organized according to the [File Structure] tab. | 3.1 | DONE
| FEMA DFIRM FLOODWAY {FEMA_fldwy.shp} Format: Polygon shapefile (OPTIONAL) | The effective FEMA floodway for the study reach, clipped to the study area. | Technical Partner will deliver layer in (1) shapefile format,(2) with FGDC compliant metadata attached by using ESRI ArcCatalog, Metadata will include elements listed in [Metadata] (3) in a WGS84 projection (4) name files according to the standard-see {bracketed} example. Data will be delivered in a zip file and organized according to the [File Structure] tab. | 3.1 | NA
| FEMA DFIRM 1% {FEMA_1pct.shp} Format: Polygon shapefile (OPTIONAL) | The effective FEMA 1% annual chance floodplain (also known as the Special Flood Hazard Area) for the study reach, clipped to the study area. | Technical Partner will deliver layer in (1) shapefile format,(2) with FGDC compliant metadata attached by using ESRI ArcCatalog, Metadata will include elements listed in [Metadata] (3) in a WGS84 projection (4) name files according to the standard-see {bracketed} example. Data will be delivered in a zip file and organized according to the [File Structure] tab. | 3.1 | NA
| FEMA DFIRM 0.2% {FEMA_02pct.shp} Format: Polygon shapefile (OPTIONAL) | The effective 0.2% annual chance floodplain (if applicable) for the study reach, clipped to the study area. | Technical Partner will deliver layer in (1) shapefile format,(2) with FGDC compliant metadata attached by using ESRI ArcCatalog, Metadata will include elements listed in [Metadata] (3) in a WGS84 projection (4) name files according to the standard-see {bracketed} example. Data will be delivered in a zip file and organized according to the [File Structure] tab. | 3.1 | NA
| FLOOD CONTROL STRUCTURES {flood_cntrl.shp} Format: Line shapefile (OPTIONAL) | The centerline of a floodwall, levee or other flood control structure. Flood control structures centerlines should agree with the geographic location of the structures, as visible from satellite photography or as documented in as-built or design documents. Review the [Structures] tab in the Project Development Template and check to ensure that all flood control structures were included in the GIS data. | Technical Partner will deliver layer in (1) shapefile format,(2) with FGDC compliant metadata attached by using ESRI ArcCatalog, Metadata will include elements listed in [Metadata] (3) in a WGS84 projection (4) name files according to the standard-see {bracketed} example. Data will be delivered in a zip file and organized according to the [File Structure] tab. | 3.1 | DONE
| LEVEE RISK AREA {levee_ risk_area.shp} Format: Polygon Shapefile (OPTIONAL) | The identified risk area on the landward (dry) side of a levee, where flood waters would cause inundation , if the levee was to overtop. | Technical Partner will deliver layer in (1) shapefile format,(2) with FGDC compliant metadata attached by using ESRI ArcCatalog, Metadata will include elements listed in [Metadata] (3) in a WGS84 projection (4) name files according to the standard-see {bracketed} example. Data will be delivered in a zip file and organized according to the [File Structure] tab. | 3.1 | NA
| DEPTH GRIDS {elev_feet_tenth} Format: ESRI Grid (REQUIRED) | Depth grids corresponding to mapped inundation areas from action stage through at least the flood of record at 1 ft intervals or less. For example, a depth grid with a water surface elevation of 78.3 feet NAVD88 at the gage would be named “elev_78_3”. Each depth grid should include the appropriate support files, with extensions # dblbnd.adf, # hdr.adf, # sta.adf; # vat.adf; #w001001.adf; # w001001x.adf | Technical Partner will deliver layer in (1) shapefile format,(2) with FGDC compliant metadata attached by using ESRI ArcCatalog, Metadata will include elements listed in [Metadata] (3) in a WGS84 projection (4) name files according to the standard-see {bracketed} example. Data will be delivered in a zip file and organized according to the [File Structure] tab. | N/A | DONE
| POLYGONS {elev_feet_tenth.shp} Format: Polygon shapefile (REQUIRED) | Mapped inundation areas from action stage through at least the flood of record at 1 ft intervals or less. For example, an inundation area with a water surface elevation of 78.3 feet NAVD88 at the gage would be named “elev_78_3.shp”. Each mapped inundation area should include the following file extensions: .dbf, .prj, .sbn, .sbx, .shp, .shp, .xml, and .shx. | Technical Partner will deliver layer in (1) shapefile format,(2) with FGDC compliant metadata attached by using ESRI ArcCatalog, Metadata will include elements listed in [Metadata] (3) in a WGS84 projection (4) name files according to the standard-see {bracketed} example. Data will be delivered in a zip file and organized according to the [File Structure] tab. | N/A | DONE
Project Documentation Deliverables
| Terrain Data (REQUIRED) | The terrain DEM that was used to process the original data. Terrain data should have metadata associated. | Technical Partner to provide terrain data. Terrain data are provided outside of zip file. See [File Structure]. | 3.1.6 | DONE
| Hydraulic Model (REQUIRED) | Include hydraulic model data (as digital files). | Technical Partner to provide hydraulic model that has passed NWS QAQC review. Model to be provided according to [File Structure] | N/A | DONE
| Final Technical Summary Document - Hydraulics & GIS (REQUIRED) | Include completed Technical Summary document with Sections 1.0, 2.0, 3.0 and 4.0 completed as specified in the [Tech Doc] tab. | Technical Partner to provide Technical Summary Document that has passed NWS QAQC review. The Technical Summary Document will be formatted according to the [Tech Doc] tab. Data will be delivered in a zip file and organized according to the [File Structure] tab. Document will be delivered in Adobe Acrobat .pdf format. | 3.5 | DONE
| Status List | Work List
| Not Started | R
| In Progress | A
| Completed | C
| Not Applicable | I

## Metadata
Metadata Requirements
Applies to:
All geospatial data submitted to NWS.
Method for Data Entry:
Use ArcGIS ArcCatalog for data entry, so that metadata file is "attached" to shapefile and grids and can be viewed with ArcGIS catalog
Populate the following information in the FGDC metadata. Lowercase text may be copied directly. UPPERCASE text should be substituted with product specific info.
Metadata Fields | STUDY AREA | MODEL CROSS-SECTIONS | GAGE LOCATION POINT | FEMA DFIRM FLOODWAY | FEMA DFIRM 1% | FEMA DFIRM 0.2% | FLOOD CONTROL STRUCTURES | LEVEE RISK AREA | DEPTH GRIDS | POLYGONS | Metadata Text to Enter
Tags: | X | X | X | [5 empty] | X | X | STATE MAP WAS PRODUCTED IN, NAME OF COMMUNITY, flood, flood inundation mapping, hydrologic prediction, hydraulic, modeling,
Summary: | X | X | X | [5 empty] | X | X | This data set was developed exclusively for use with the National Weather Service's (NWS) Advanced Hydrologic Prediction Service (AHPS) website.
Description (Abstract): | X | X | X | [5 empty] | X | X | DESCRIBE THE DATA SET. The Flood Inundation Map Graphics show the lateral extent of projected flooding on local map backgrounds.
Credits: | X | X | X | [5 empty] | X | X | XXXX agency conducted the hydraulic analysis and GIS analysis to produce the inundation data. NWS provided the QA\QC review of the data. Funding was received from XXXX for this project.
Use limitations: | X | X | X | [5 empty] | X | X | Users must assume responsibility to determine the appropriate use of this data. Users should be aware of the limitations of this dataset if using for critical application. Flood Inundation Maps will show the extent of flooding expected spatially over a given area. This will indicate when roadways, streets, buildings, airports, etc. are likely to be impacted by floodwaters. The accuracy of the mapping depends on the degree of accuracy of DEM data available for use in the GIS application, plus other factors.
Purpose | X | X | X | [5 empty] | X | X | This data set was developed for use with the National Weather Service's (NWS) Advanced Hydrologic Prediction Service (AHPS) website
Audience: | X | X | X | [5 empty] | X | X | The initial target audience is the state and local agencies that must make emergency operational decisions during flooding events. However, since the graphics are easy to view, anyone with an interest during these events can make use of the maps, including the Federal Emergency Management Agency (FEMA), the U.S. Geological Survey (USGS), Corps of Engineers (COE), state and local emergency managers, the media, and the general public.
Date of Publication: | X | X | X | [5 empty] | X | X | DATE AND YEAR
Contact Info: | X | X | X | [5 empty] | X | X | Comments regarding the Flood Inundation Maps can be made here (http://www.weather.gov/survey/nws-survey.php?code=inundate). CONTACT INFO FOR AGENCY THAT PRODUCED THE DEPTH GRID AND POLYGONS.
Horizontal Datum: | X | X | X | [5 empty] | X | X | World Geodetic System of 1984
Vertical Datum: | [8 empty] | X | X | NAVD 88
Horizontal Accuracy: | [8 empty] | X | X | As with any engineering analysis of this type, variation from the estimated flood heights and floodplain boundaries is possible. Details of the process used to produce this data can be found in project documentation available from the data contact person. Horizontal accuracy was tested by evaluating boundaries to best available topographic dataset.
Vertical Accuracy: | [8 empty] | X | X | As with any engineering analysis of this type, variation from the estimated flood heights and floodplain boundaries is possible. Details of the process used to produce this data can be found in project documentation available from the data contact person. Vertical accuracy was tested by evaluating boundaries to best available topographic dataset

## File Structure
File Structure Requirements
Deliverables by Phase |  |  |  | AHPS Deliverables - Standard Directory Format
Phase 1 | Phase 2A | Phase 2B | Phase 3
X | X | X | X | NWSLID.MM.DD.YYYY. Zip | (ex: IOWI4.01.22.12.zip)
\hydraulics\
| X |  |  |  |  | Hydraulic Model Files
\GIS\
\depth_ grids\
|  | X |  |  |  |  | raster_elev_feet_tenth
|  | X |  |  |  |  | …raster_elev_feet_tenth
\polygons\
|  | X |  |  |  |  | elev_feet_tenth.shp
|  | X |  |  |  |  | …elev_feet_tenth.shp
\base_data\
X |  | X** |  |  |  |  | study_area.shp
X | X** | [5 empty] | xs.shp
X |  | X** |  |  |  |  | gage.shp
\documentation\
|  |  | X |  |  | Project Development Template.xls
X | X** | X** |  |  |  | Technical Summary Document.pdf
| X |  |  |  |  | Rating Curve Extension Text File (OPTIONAL)
|  |  | X |  |  | Any Supplemental Documentation
Additional Deliverables - Outsize of Zip File
|  | X |  | Terrain Data
(**indicates updated data)